# 4. Project Planning Phase

The Project Planning Phase defines how the AI WeatherWise API is organised, scheduled and delivered. The work is divided into clear milestones and sprints that follow the five epics of this document: Project Architecture, Project Setup and Configuration, Backend Development, Database Configuration and Project Execution. Each sprint has a fixed goal, a set of tasks and a measurable deliverable, so progress can be tracked from the first requirement to the final API demonstration.

## Planning Objectives

- Scope Definition: Deliver a secure REST API for user authentication, favorite location management, real-time weather retrieval and Gemini AI-based summaries and recommendations.

- Incremental Delivery: Build the system in small sprints so that every sprint ends with a working, testable part of the backend.

- Risk Control: Identify technical risks early, such as missing API keys, database connection failures and unauthorized access, and plan safeguards for them.

- Quality Assurance: Verify every endpoint in Postman before it is marked as complete.

## Milestones and Activities

| Milestone | Activities | Deliverable |
| --- | --- | --- |
| Milestone 1: Requirement Analysis and Architecture Design (Epic 1) | - Identify user problems and define the scenario-based case study. - List software and hardware requirements. - Design the MVC architecture, ER diagram and user flow. | Architecture diagram, ER diagram and user flow diagram |

| Milestone | Activities | Deliverable |
| --- | --- | --- |
| Milestone 2: Project Setup and Configuration (Epic 2) | - Create the AI Weatherwise project folder in Visual Studio Code. - Initialize Node.js and install Express, Mongoose, bcryptjs, jsonwebtoken, cors, dotenv and the Gemini SDK. - Create index.js, .env and .gitignore, and set up the folder structure. | Working project skeleton with environment configuration |
| Milestone 3: Database Configuration (Epic 4) | - Establish the MongoDB connection using Mongoose. - Create the User and Location schemas and models. - Apply validation rules, unique email constraint and the User to Location reference. | Connected database with validated schemas |
| Milestone 4: Backend Development (Epic 3) | - Build register and login APIs with bcrypt hashing and JWT tokens. - Implement authentication and role-based middleware. - Develop CRUD APIs for favorite locations. - Integrate the weather service and the Gemini AI insight and recommendation service. - Add fallback mode, centralized error handling and request sanitization. | Complete set of secured REST API endpoints |

| Milestone | Activities | Deliverable |
| --- | --- | --- |
| Milestone 5: Testing, Execution and Documentation (Epic 5) | - Run the server locally and test Register, Login, Weather and Recommendation APIs in Postman. - Record the API testing and backend demo videos. - Prepare the final documentation and upload the code. | Tested API, demo videos, final documentation and source code |

## Sprint Planning

The project follows an Agile approach with four one-week sprints. Story points show the relative effort of each sprint (1 point is a very small task, 13 points is a large one).

| Sprint | Duration | Tasks / User Stories | Story Points | Epic |
| --- | --- | --- | --- | --- |
| Sprint 1 | Week 1 | Analyse requirements and define the problem statement. Design the architecture, ER diagram and user flow. Create the project folder, install dependencies and configure .env. | 8 | Epic 1 and Epic 2 |
| Sprint 2 | Week 2 | Connect the MongoDB database. Create the User and Location schemas. Develop register and login with password hashing and JWT. Build the authentication middleware. | 13 | Epic 4 and Epic 3 (part 1) |

| Sprint | Duration | Tasks / User Stories | Story Points | Epic |
| --- | --- | --- | --- | --- |
| Sprint 3 | Week 3 | Develop favorite location CRUD APIs. Integrate real-time weather data. Integrate Gemini AI for summaries and recommendations. Add fallback mode, error handling and sanitization. | 13 | Epic 3 (part 2) |
| Sprint 4 | Week 4 | Test all endpoints in Postman. Fix defects found during testing. Record demo videos and finalize documentation. | 8 | Epic 5 |

Total planned effort: 42 story points, an average velocity of about 10 story points per sprint.

## Project Timeline

| Week | Focus | Outcome |
| --- | --- | --- |
| Week 1 | Requirements, architecture and project setup | Design diagrams and project skeleton ready |
| Week 2 | Database and authentication | Users can register and log in securely |
| Week 3 | Location, weather and AI features | Weather insights and recommendations working |
| Week 4 | Testing, demo and documentation | Final submission package ready |

## Roles and Task Allocation

- Developer: Designs the architecture, writes the backend code, configures the database and integrates the weather and Gemini AI services.

- Tester: Validates each API in Postman, checks status codes, JWT protection and error responses.

- Documentation Owner: Prepares diagrams, screenshots, API testing evidence, demo videos and the final report.

## Tools Used for Planning and Tracking

- Visual Studio Code: Code development and project structure management.

- Postman / Thunder Client: API testing and response verification.

- MongoDB: Database storage and verification of saved users and locations.

- Git and GitHub: Version control and code backup.

- Google Drive: Storage of the source code, testing video and demo video.

## Risk Assessment and Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Missing or invalid external API keys | Weather or AI responses fail | Fallback mode keeps the API functional without external keys |
| Database connection failure | Server cannot store or read data | Server starts only after a successful MongoDB connection, with clear error logs |
| Unauthorized access | Private user data exposed | JWT authentication, bcrypt password hashing and role-based route guarding |

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Malicious input (XSS / NoSQL injection) | Data corruption or security breach | Request sanitization and Mongoose schema validation |
| Third-party API rate limits or downtime | Delayed or incomplete responses | Centralized error handling with meaningful error messages |

## Deliverables

- Architecture, ER and user flow diagrams.

- Configured Node.js project with MongoDB connection and environment variables.

- Secure REST APIs: Register, Login, Favorite Locations, Weather and AI Recommendation.

- Postman API testing screenshots and testing video.

- Backend demo video, complete source code and final project documentation.